## Actions
GAME BREAKDOWN TASK LIST
Team Four |  |  | Last Updated: | 2019-10-16
DONE? | TASK | IMPORTANCE | OWNER | STARTED | FINISHED | NOTES / DESCRIPTION
ART DEPARTMENT
TRUE | head/helemt |  |  | 2019-10-16 | 2019-10-17
TRUE | body (charcater) |  |  | 2019-10-16 | 2019-10-17
TRUE | legs |  |  | 2019-10-16 | 2019-10-17
FALSE | sword |  |  | 2019-10-16
FALSE | wings |  |  | 2019-10-16
FALSE | body (fly) |  |  | 2019-10-16
FALSE | base |  |  | 2019-10-16
TRUE | body (windmill) |  |  | 2019-10-16 | 2019-10-17
TRUE | windmill blades |  |  | 2019-10-16 | 2019-10-17 | spirte
TRUE | chacter walking |  |  | 2019-10-16 | 2019-10-17 | legs moving back and forth
FALSE | chacter jumping |  |  | 2019-10-16 |  | charcter juming up and down legs moving out
FALSE | fly |  |  | 2019-10-16 |  | wings moving in and out
TRUE | Big tree |  |  | 2019-10-16 | 2019-10-17 | first tree you see
TRUE | Other big tree |  |  | 2019-10-16 | 2019-10-17 | last tree you see
TRUE | Smallest tree (transparent) |  |  | 2019-10-16 |  | in front of the forth fly
TRUE | medium tree |  |  | 2017-10-16 | 2019-10-17 | second tree
FALSE | mountains |  |  | 2019-10-16 |  | 3 of them and pointy
TRUE | wagon |  |  | 2019-10-16 | 2019-10-17 | facing right
TRUE | clouds x3 |  |  | 2019-10-16 |  | all drifferent but specific shapes
FALSE | flowers x7 |  |  | 2019-10-16
TRUE | middle groud bushes |  |  | 2019-10-16 | 2019-10-17
FALSE | foreground bushes (light) |  |  | 2019-10-16
FALSE | foreground bushes (dark) |  |  | 2019-10-16
TRUE | grass |  |  | 2019-10-16 | 2019-10-17
TRUE | training dummy |  |  | 2019-10-16 | 2019-10-17
DESIGN DEPARTMENT
FALSE | Fly 1 movement | HIGH
FALSE | Fly 2 movement | HIGH
FALSE | Fly 3 movement | HIGH
FALSE | Fly 4 movement | HIGH
FALSE | Fly 5 movement | HIGH
FALSE | Fly boss movement | HIGH
TRUE | Level layout | HIGH | Sammy | 2019-10-16 | 2019-10-17
TRUE | Player Jumping height | HIGH
TRUE | Player running speed | MEDIUM
TRUE | Fly hit points | MEDIUM
TRUE | boss fly hit points | MEDIUM
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
SOUND DEPARTMENT
TRUE | Menu Song |  |  | 2019-10-16
TRUE | Menu Ambiance |  |  | 2019-10-16 |  | (Wind, Flies Buzzing, Chirping)
TRUE | Button Click |  |  | 2019-10-16
TRUE | Player Taking Damage |  |  | 2019-10-16 |  | This sound is the same as the Button
TRUE | Player on Grass Sound |  |  | 2019-10-16 |  | This sound only occurs when player has stopped moving
TRUE | Player Jumping |  |  | 2019-10-16
TRUE | Normal Flies/Enemies taking damage |  |  | 2019-10-16 |  | Normal Flies and Taking Damage are seperate sounds. Both have been found
FALSE | Boss Fly taking damage |  |  | 2019-10-16 |  | Lower pitch version of the Normal Fly
TRUE | Gameplay Level Song |  |  | 2019-10-16
TRUE | Windmill Movement Sound (Blades) |  |  | 2019-10-16
TRUE | Level Exit / Door Sound |  |  | 2019-10-16
TRUE | Player Death |  |  | 2019-10-16
TRUE | End Game Music |  |  | 2019-10-16 |  | Same as Menu Song
TRUE | Game Over Music |  |  | 2019-10-16 |  | Same as Menu and End Song
TRUE | Dummy taking Damage
TRUE | Dummy dying
TRUE | Normal Enemy Dying
FALSE | Boss Dying |  |  |  |  | Lower Pitch of Fly Dying
FALSE
FALSE
TECH DEPARTMENT
TRUE | Player Movement | HIGH |  |  |  | (Jump, Left, Right)
TRUE | Camera Movement | HIGH |  |  |  | (Follows Player, Controls Background Movement)
TRUE | Hitbox Collision | HIGH
TRUE | End Goal | HIGH
TRUE | UI | LOW
FALSE | Player and Enemy Spawning | HIGH
TRUE | Enemy Pathing | MEDIUM
TRUE | Health | MEDIUM
TRUE | Windmill | MEDIUM
FALSE
TRUE | CameraMove.cs
TRUE | ChangeLevelOnCollide.cs
TRUE | CreateEventFunction.cs
TRUE | DamageOnCollide.cs
TRUE | DelayedSceneChange.cs
TRUE | FlyDeath.cs
TRUE | Health.cs
TRUE | HealthBar.cs
TRUE | Mantle.cs
TRUE | Paralax.cs
TRUE | PathEnemy.cs
TRUE | Player.cs
TRUE | WindMill.cs
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE